## Production Timeline
HEARTH · Indie Film Production Timeline
| Project Title: |  | Format: |  | Shoot Days: |  | Use this column for target dates →
| Week | Milestone / Task | Phase | Owner | Depends On | Status | Target Date / Notes
── DEVELOPMENT ──
| 1 | Concept and story idea locked | Development | [Assign] | — | Not Started | What is the film about in one sentence?
| 1-2 | Script first draft complete | Development | [Assign] | Concept | Not Started | First full draft — do not show anyone yet
| 2 | Script notes and feedback round | Development | [Assign] | First Draft | Not Started | Two trusted readers maximum
| 3 | Script revision complete | Development | [Assign] | Notes | Not Started | Address structural issues before moving to pre-prod
| 3 | Identify core team (Producer, DP) | Development | [Assign] | Script Draft | Not Started | These relationships determine everything
| 3-4 | Budget first pass complete | Development | [Assign] | Script Rev | Not Started | Use HEARTH budget template
| 4 | Funding secured or committed | Development | [Assign] | Budget | Not Started | No shoot without a funded budget
| 4 | Production insurance quote obtained | Development | [Assign] | Budget | Not Started | ⚠ Required before any shoot can proceed
── PRE-PRODUCTION ──
| 5 | Location scout and lock all locations | Pre-Production | [Assign] | Budget | Not Started | Confirm permits required for each location
| 5 | Casting breakdown published | Pre-Production | [Assign] | Script Final | Not Started | Submit to Actors Access and casting platforms
| 5-6 | Auditions and callbacks | Pre-Production | [Assign] | Casting BD | Not Started | Record auditions for review
| 6 | Cast locked — all roles confirmed | Pre-Production | [Assign] | Auditions | Not Started | Signed contracts and releases before shoot
| 6 | Department heads hired (Gaffer, Sound, Art) | Pre-Production | [Assign] | Budget | Not Started | All contracts signed before first prep day
| 6 | Location permits submitted | Pre-Production | [Assign] | Locations | Not Started | Allow 2-3 weeks for permit processing
| 6-7 | Shot list and storyboards complete | Pre-Production | [Assign] | Script Final | Not Started | Essential prep — do not skip
| 7 | Equipment package confirmed | Pre-Production | [Assign] | Budget | Not Started | Confirm rental house and reserve equipment
| 7 | Art department prep begins | Pre-Production | [Assign] | Locations | Not Started | Props, wardrobe, set dressing
| 7 | Production insurance confirmed | Pre-Production | [Assign] | Quote | Not Started | ⚠ POLICY IN HAND BEFORE SHOOT DAY
| 7 | Call sheet template built | Pre-Production | [Assign] | Schedule | Not Started | Build daily call sheet from HEARTH template
| 7-8 | Rehearsals with principal cast | Pre-Production | [Assign] | Cast Locked | Not Started | Minimum one rehearsal per scene
| 8 | Final budget signed off | Pre-Production | [Assign] | All Hires | Not Started | No changes after this point without approval
| 8 | Locations walkthrough with crew | Pre-Production | [Assign] | Locations | Not Started | Tech scout — all dept heads present
| 8 | All releases and contracts signed | Pre-Production | [Assign] | All Hires | Not Started | Cast and crew releases, location agreements
── PRODUCTION ──
| 9 | Shoot Day 1 | Production | [Assign] | Full Prep | Not Started | Get to set early. First shot sets the tone.
| 9 | Daily footage backup — on-set and off-site | Production | [Assign] | Each shoot day | Not Started | Two drives minimum. One leaves the location.
| 9 | Daily call sheet distributed by 1AD | Production | [Assign] | Previous day wrap | Not Started | Send night before. Confirm crew receipt.
| 9-10 | Shoot Days 2 through [X] | Production | [Assign] | Shoot Day 1 | Not Started | Stay on schedule. Address problems same day.
| 10 | Production WRAP | Production | [Assign] | Final shoot day | Not Started | ⚠ Secure all footage before releasing location
| 10 | Equipment returned to rental house | Production | [Assign] | Wrap | Not Started | Check for damage before return
| 10 | Final production report from 1AD | Production | [Assign] | Wrap | Not Started | Document actual pages shot per day
── POST-PRODUCTION ──
| 11 | All footage ingested and organized | Post-Production | [Assign] | Wrap | Not Started | Label and log all footage before first cut
| 11-12 | Assembly cut (editor's first pass) | Post-Production | [Assign] | Ingest | Not Started | No director notes until assembly is complete
| 12-13 | Director cut with notes | Post-Production | [Assign] | Assembly | Not Started | Work in rounds — do not cut endlessly
| 13-14 | Picture lock | Post-Production | [Assign] | Dir Cut | Not Started | ⚠ No changes after picture lock. Everything downstream depends on this.
| 14 | Sound design and mix begins | Post-Production | [Assign] | Picture Lock | Not Started | Music temp track can begin here
| 14 | Color grade begins | Post-Production | [Assign] | Picture Lock | Not Started | Work from a grade reference if possible
| 15 | Music secured — score or licensing | Post-Production | [Assign] | Picture Lock | Not Started | All music must be cleared before delivery
| 15 | Closed captions / subtitles created | Post-Production | [Assign] | Picture Lock | Not Started | Required for most streaming and distribution
| 16 | Sound mix complete | Post-Production | [Assign] | Sound Design | Not Started | Final mix to broadcast specs
| 16 | Color grade complete | Post-Production | [Assign] | Color Grade | Not Started | Final grade approved by director
| 17 | Deliverables created | Post-Production | [Assign] | Mix + Grade | Not Started | DCP, ProRes master, web versions, festival specs
| 17 | EPK (Electronic Press Kit) assembled | Post-Production | [Assign] | Wrap Photos | Not Started | Stills, synopsis, director bio, film still selects
| 17 | Final backup — all masters archived | Post-Production | [Assign] | Deliverables | Not Started | ⚠ Store on two separate hard drives in two locations
── DISTRIBUTION ──
| 18 | Festival strategy confirmed | Distribution | [Assign] | Deliverables | Not Started | Which festivals, which premiere, in what order
| 18 | Filmfreeway account set up | Distribution | [Assign] | Strategy | Not Started | Create account and upload all materials
| 18-20 | Festival submissions — Tier 1 | Distribution | [Assign] | Filmfreeway | Not Started | World premiere at the highest tier reachable
| 20+ | Festival submissions — Tier 2 and 3 | Distribution | [Assign] | Tier 1 Results | Not Started | Expand based on Tier 1 responses
| Rolling | Vimeo Staff Pick submission | Distribution | [Assign] | Deliverables | Not Started | Free. Upload and pitch to curation team separately
| Rolling | MUBI submission | Distribution | [Assign] | Deliverables | Not Started | Apply directly. HEARTH preferred partner.
| Rolling | Community screenings and direct distribution | Distribution | [Assign] | Deliverables | Not Started | Take the film to the community it is about
⚠ = Critical milestone — do not proceed to next phase without completing this task ¦ Red rows = gates that block production
HEARTH · Production Resource Library · buildyourhearth.studio

## Short Film — 8 Week Plan
HEARTH · Short Film 8-Week Quick Plan
Week | Primary Focus | Key Deliverable | Notes
1 | Script locked + core team hired | Final script, DP and producer confirmed | Budget first pass due end of week
2 | Locations and cast | All locations confirmed, casting in progress | Permits submitted this week
3 | Casting locked + full crew hired | Signed contracts for all cast and crew | Location agreements signed
4 | Shot list, rehearsals, equipment | Complete shot list, all rehearsals done | Equipment reserved and confirmed
5 | SHOOT | All footage captured | Two-drive backup every day. No exceptions.
6 | Assembly cut | Editor's assembly cut complete | Director reviews — do not give notes until done
7 | Director cut + picture lock | Picture lock achieved | Sound and color begin this week
8 | Post complete + deliverables | Mix, grade, deliverables, EPK in hand | Submit to Filmfreeway this week